## Sheet1
Autonomus Green House system
Information Technology Institute(ITI) |  |  |  |  | Project Start: | 2023-05-06
Embedded Systems New Capital G2 |  |  |  |  | Week 1 | [6 empty] | Week2 | [6 empty] | Week 3
[5 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TASK | ASSIGNED | PROGRESS | START | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Documentation / Business Case document | ME, MM, MS, SM,YH |  | 2023-06-05 | 2023-06-21 | bar: Week 1 5 to Week 3 21
Project main goal | Mostafa Essam |  | 2023-06-05 | 2023-06-06 | bar: Week 1 8 to Week 1 9
Project application | Youssef Hesham |  | 2023-06-06 | 2023-06-07 | bar: Week 1 9 to Week 1 10
Products features | Mohamed Tharwat |  | 2023-06-06 | 2023-06-07 | bar: Week 1 9 to Week 1 10
Required H.W | Saad Mohamed |  | 2023-06-09 | 2023-06-11 | bar: Week2 12 to Week2 14
Gantt Chart | MM, MS |  | 2023-06-05 | 2023-06-21 | bar: Week 1 11 to Week2 12; Week 3 19 to Week 3 21
Implement the code of the microcontroller | SM, YH |  | 2023-06-12 | 2023-06-23 | bar: Week2 12 to Week 3 23
Testing With hardware | SM, YH |  | 2023-06-14 | 2023-06-23 | bar: Week2 14 to Week2 16; Week 3 20 to Week 3 23
Hardware model and Fabrication | MS, MT,ME |  | 2023-06-14 | 2023-06-20 | bar: Week2 14 to Week 3 20
PCB Design | Mohamed Tharwat |  | 2023-06-14 | 2023-06-17 | bar: Week2 14 to Week2 17
Model Casing | MS, ME |  | 2023-06-16 | 2023-06-20 | bar: Week2 16 to Week 3 20
Implement GUI and HMI with rspi | Saad Mohamed |  | 2023-06-18 | 2023-06-22 | bar: Week2 18 to Week 3 22
Presentation and Rehearsal | ME, MM, MS, SM,YH |  | 2023-06-22 | 2023-06-23 | bar: Week 3 22 to Week 3 23